## Week of 12-7-2015
KSU CUP Package E Method of Procedure CBC FCU's
Superintendent: Ian Wood SPE: Whitney Henle Field Engineer: Coleman Henry
|  |  |  | Mon 2/29 |  | Tues |  | Wed |  | Thurs |  | Fri |  |  |  | Mon 3/7 |  | Tues |  | Wed |  | Thurs |  | Fri |  |  |  | Mon 3/14 |  | Tues |  | Wed |  | Thurs |  | Fri |  |  |  | Mon |  | Tues |  | Wed |  | Thurs |  | Fri
|  |  |  | Mon | Night | Tues | Night | Wed | Night | Thurs | Night | Fri | Sat | Sun | Comments/Materials/ resources/delays | Mon | Night | Tues | Night | Wed | Night | Thurs | Night | Fri | Sat | Sun | Comments/Materials/ resources/delays | Mon | Night | Tues | Night | Wed | Night | Thurs | Night | Fri | Sat | Sun | Comments/Materials/ resources/delays | Mon | Night | Tues | Night | Wed | Night | Thurs | Night | Fri | Sat | Sun
Chem/BioChem
Fan Coil Unit Method of Procedures
Third Floor
Advanced Notice to Users
Chilled Water Shutdown Notification
Heating Hot Water Shutdown Notification
|  |  | Isolation of 3rdst Floor CW | [6 empty] | X
|  |  | Draining 3rd Floor CW | [6 empty] | X
|  |  | Isolation of 3rd Floor HW | [6 empty] | X
|  |  | Draining 3rd Floor HW | [6 empty] | X
EL002, 352, 201, 301A, 303, 303A,
Steps for Removal
|  |  | User equipment moved/relocated |  |  |  |  | X | [6 empty] | ROOMS FED FROM 2ND FLOOR
|  |  | LOTO Circuit Breaker |  |  |  |  | X
|  |  | Disconnection of FCU's electrical |  |  |  |  | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [5 empty] | X
|  |  | Remove Existing FCU Cabinet | [5 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [5 empty] | X
|  |  | Installation of new HW Contol Valve | [5 empty] | X
|  |  | Installation of new FCU Cabinet | [5 empty] | X
|  |  | Installation of Iso Valve for High-Eff Unit. | [5 empty] | X
|  |  | Provide power to new FCU | [6 empty] | X
|  |  | Connection of New Thermostat | [6 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [6 empty] | X
|  |  | Insulation of new Piping and Valves | [12 empty] | X
User equipment place back in position
307, CR302, 308, 309, 311*
Steps for Removal
|  |  | User equipment moved/relocated | [6 empty] | X
|  |  | LOTO Circuit Breaker | [6 empty] | X
|  |  | Disconnection of FCU's electrical | [6 empty] | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [7 empty] | X
|  |  | Remove Existing FCU Cabinet | [7 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [7 empty] | X
|  |  | Installation of new HW Contol Valve | [7 empty] | X
|  |  | Installation of new FCU Cabinet | [7 empty] | X
|  |  | Provide power to new FCU | [7 empty] | X
|  |  | Connection of New Thermostat | [8 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [8 empty] | X
|  |  | Insulation of new Piping and Valves | [8 empty] | X | [5 empty] | X
User equipment place back in position
313*, 312, 314, 316
Steps for Removal
|  |  | User equipment moved/relocated | [12 empty] | X
|  |  | LOTO Circuit Breaker | [12 empty] | X
|  |  | Disconnection of FCU's electrical | [12 empty] | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [13 empty] | X
|  |  | Remove Existing FCU Cabinet | [13 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [13 empty] | X
|  |  | Installation of new HW Contol Valve | [13 empty] | X
|  |  | Installation of Iso Valve for High-Eff Unit. | [13 empty] | X
|  |  | Installation of new FCU Cabinet | [13 empty] | X
|  |  | Provide power to new FCU | [14 empty] | X
|  |  | Connection of New Thermostat | [14 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [14 empty] | X
|  |  | Insulation of new Piping and Valves | [16 empty] | X
User equipment place back in position
317, 318, 319, CR301, 322, 322A, 323A
Steps for Removal
|  |  | User equipment moved/relocated | [14 empty] | X
|  |  | LOTO Circuit Breaker | [14 empty] | X
|  |  | Disconnection of FCU's electrical | [14 empty] | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [15 empty] | X
|  |  | Remove Existing FCU Cabinet | [15 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [15 empty] | X
|  |  | Installation of new HW Contol Valve | [15 empty] | X
|  |  | Installation of new FCU Cabinet | [15 empty] | X
|  |  | Provide power to new FCU | [15 empty] | X
|  |  | Connection of New Thermostat | [16 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [16 empty] | X
|  |  | Insulation of new Piping and Valves | [16 empty] | X |  | X
User equipment place back in position
|  |  | Reintroduce Chilled Water for Hydrostatic Test | [11 empty] | Verify no leaks, shutoff water |  |  |  |  | X
|  |  | Reintroduce Heating Hot Water for Hydrostatic Test | [16 empty] | X
|  |  | Isolation of 3rd Floor CW | [16 empty] | X
|  |  | Draining 3rd Floor CW | [16 empty] | X
|  |  | Isolation of 3rd Floor HW | [16 empty] | X
|  |  | Draining 3rd Floor HW | [16 empty] | X
User equipment place back in position
323, 327, 328, 329, LB301, 331
Steps for Removal
|  |  | User equipment moved/relocated | [16 empty] | X
|  |  | LOTO Circuit Breaker | [16 empty] | X
|  |  | Disconnection of FCU's electrical | [16 empty] | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [17 empty] | X
|  |  | Remove Existing FCU Cabinet | [17 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [17 empty] | X
|  |  | Installation of new HW Contol Valve | [17 empty] | X
|  |  | Installation of Iso Valve for High-Eff Unit. | [17 empty] | X
|  |  | Installation of new FCU Cabinet | [17 empty] | X
|  |  | Provide power to new FCU | [18 empty] | X
|  |  | Connection of New Thermostat | [18 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [18 empty] | X
|  |  | Insulation of new Piping and Valves | [20 empty] | X
User equipment place back in position
CR305, 333, 336, 338, 341
Steps for Removal
|  |  | User equipment moved/relocated | [18 empty] | X
|  |  | LOTO Circuit Breaker | [18 empty] | X
|  |  | Disconnection of FCU's electrical | [18 empty] | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [19 empty] | X
|  |  | Remove Existing FCU Cabinet | [19 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [19 empty] | X
|  |  | Installation of new HW Contol Valve | [19 empty] | X
|  |  | Installation of new FCU Cabinet | [19 empty] | X
|  |  | Provide power to new FCU | [19 empty] | X
|  |  | Connection of New Thermostat | [20 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [20 empty] | X
|  |  | Insulation of new Piping and Valves | [20 empty] | X |  |  |  | X
User equipment place back in position
343, 346, 348, 351
Steps for Removal
|  |  | User equipment moved/relocated | [24 empty] | X
|  |  | LOTO Circuit Breaker | [24 empty] | X
|  |  | Disconnection of FCU's electrical | [24 empty] | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [25 empty] | X
|  |  | Remove Existing FCU Cabinet | [25 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [25 empty] | X
|  |  | Installation of new HW Contol Valve | [25 empty] | X
|  |  | Installation of Iso Valve for High-Eff Unit. | [25 empty] | X
|  |  | Installation of new FCU Cabinet | [25 empty] | X
|  |  | Provide power to new FCU | [26 empty] | X
|  |  | Connection of New Thermostat | [26 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [26 empty] | X
|  |  | Insulation of new Piping and Valves | [28 empty] | X
User equipment place back in position
334, 337*, 339, 342, 344, 347, 349
Steps for Removal
|  |  | User equipment moved/relocated | [26 empty] | X
|  |  | LOTO Circuit Breaker | [26 empty] | X
|  |  | Disconnection of FCU's electrical | [26 empty] | X
|  |  | Possible demo of ceiling tile, carpet, and drywall | [27 empty] | X
|  |  | Remove Existing FCU Cabinet | [27 empty] | X
Steps for Reinstall
|  |  | Installation of new CW Control Valve | [27 empty] | X
|  |  | Installation of new HW Contol Valve | [27 empty] | X
|  |  | Installation of new FCU Cabinet | [27 empty] | X
|  |  | Provide power to new FCU | [27 empty] | X
|  |  | Connection of New Thermostat | [28 empty] | X
|  |  | Dry Valve Actuator Stroke Test | [28 empty] | X
|  |  | Insulation of new Piping and Valves | [28 empty] | X |  | X
User equipment place back in position
|  |  | Reintroduce Chilled Water for Hydrostatic Test | [23 empty] | Verify no leaks, turn off CW, leave HW on |  |  |  |  | X
|  |  | Reintroduce Heating Hot Water for Hydrostatic Test | [28 empty] | X
|  |  | Reintroduce Chilled Water | [28 empty] | X
|  |  | Verification of Functional Test | [29 empty] | X | X
*Isolation Valves Only
|  |  |  | X | New Date of Work